## Sheet1
SCRUM TASK – LOGIN AND REGISTER
USER STORY ID: 1 & 2
TASK ID	MOSCOW	TASK	Internal/External	USER STORY	PRIORITY	PLANNED HOURS	REMAIN HOURS	ACTUAL HOURS	WORK TYPE	GROUP	ASSIGNED TO	STATUS	BLOCKED	SHORT DESCRIPTION	LONG DESCRIPTION	NOTES
1	Must have	Organise Logo	External	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	8	0	0	0	Outwork	Management	Dave	Due for review 08/08/24	wait	Design work for Logo	Design of Logo for QA Restaurant has been outworked to Swan Designs due for customer review 08/08/24 – final sign off on design by 12/08/24	Wait is outwork – Affects Frontend Design
2	Must have	Create Test Database	Internal	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	1	2	0	1	Data	Data Analytics Team	Sue	Done	No	Simple test database with a customer table	Design and implement a simple MySQL test database “test_db” – Fields: customer_ID (PRIMARY AUTO-INCREMENT), customer_name, password,email, address.
3	Must have	Set up a Dev Environment	Internal	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	1	2	0	1.5	Development	Dev Team	Richard	Done	No	Project set up	JSP Project – Set up Maven Project - Tomcat v10.1, Servlet V6.1 , Create Git Repository
4	Must Have	Implement JSP pages	Internal	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	2	8	-4	12	Development	Dev Team	Nicky	Done	No	Implement JSP Pages	Register.jsp – Register Form to take customer details and add them to the database. On success creates session and redirects them to Login page. Login.jsp has Login Form & Link to Register page, Login.jsp – Connects to database and validates user. On success creates session and redirects them to welcome page Welcome.jsp. page displaying a personalised welcome, courses table and a link to logout. On logout redirects to a Goodbye page. Goodbye.jsp – ends session.	Lost a little time as Tomcat was duplicating display of JSP pages. Issue traced to Tomcats/Apache-Tomcat-10.1.15/Conf/server.xml – Duplicate entry for Servlet. (Time to trace error approx 3 hrs)
5	Must Have	GUI Enhancement	Internal	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	3	16	16	0	Frontend Design	Web Dev	Joey	not started	wait			Wait – Work can be started but cannot be completed until after Logo sign off on 12/08/24
6	Must have	Data Validation	Internal	USER STORY ID: 1 & 2, MOSCOW: Must have, As a Customer: I want to Register and Login	2	24	24	T.B.C	Development	Dev Team	Richard/Joe	not started		Implement username & password validation	Implement username & password validation using Bcrypt	Assign to Richard as he has prior experience pair up with joe for on job training
7
8
9
10