# Designing Software

# Day 1 Lab - Agile Food Delivery App

## Scenario

Acme is building a food delivery app similar to Uber Eats.

## Constraints

- 4 developers per team

- 3 month MVP deadline

- Limited budget

- Mobile first

## Team setup (5 mins)

Assign roles:

- Product Owner

- Scrum Master

- Developers

👉 Everyone contributes, but:

- Product Owner decides priority

- Scrum Master keeps team on track

## Lab structure (3 hours)

| Section | Topic | Time |
| --- | --- | --- |
| 1 | Agile planning | 30 mins |
| 2 | User stories | 60 mins |
| 3 | Backlog + prioritisation | 30 mins |
| 4 | Sprint planning | 40 mins |
| 5 | Customer journey | 20 mins |
| 6 | Review / feedback | 20 mins |

## Lab 1: Agile Planning (30 mins)

Objective

Understand how your team will run the project using Agile.

## Tasks: 1. Why Agile?

Discuss and write:

- Why Agile suits this project

- What problems it solves

👉 Prompt:

- Requirements changing?

- Need fast delivery?

- Limited budget?

## 2. Define key Agile concepts

Write short definitions (1–2 lines each):

- Sprint

- Backlog

- User story

- Increment

- Definition of Done

## 3. Decide how your team will work

Define:

- Sprint length (1 or 2 weeks)

- Number of sprints in 3 months

- What “Done” means

👉 Example Definition of Done:

- Feature works

- Meets acceptance criteria

- Tested

## Output

- Short summary (150–200 words)

- Bullet list of decisions